- Technical specification Conformity -

  - Source of Sand with specification –

- For Concrete – Gopi Ballabhpur Coarse Sand

- For Paver Block Laying – Medinipur Fine Sand

  - Make of Cement – Ambuja / Ultratech / Lafarge

  - Make of Steel – TATA / SAIL / Jindal / Shyam Steel

  - Aggregate Grade & Source – 5834 Grade - Pakur (Bhirbhum)

  - Paver Block – Automatic Hydraulic machine

  - WMM (Weight Mix Macadum) by Ready mix machine at site / as per IRC:109/1997

  - Third Party Testing of Paver Block from Approved Lab

  - Design mix of Concrete of Paver Block tested / Validate from Jadavpur University.

  - List of T&P required for the Job with quantity.

- Commercial Terms -

  - Payment terms – Within 30 days from the date of submission of Certified RA bill

  - Security Deposit –

- 10% for the total value of Contracts shall have to be deposited by the Contractor as security deposit with the Owner & retained by the Owner until the expiry of defect liability period. This would be in the form of irrevocable and unconditional performance bank guarantee as per the owner’s format & shall be submitted within 01 month of mobilization.

OR

- Alternatively the Contractor may have option to get deduct 10% of monthly RA bill as a retention amount. This shall be retained until expiry of defect liability period. This option shall be purely at discretion of owner.

  - Defect Liability period / Maintenance Period for 03 years on successful handing over of Assigned job.

  - Job Completion Time – Within 06 months from the date of Work Order.

  - LD shall be applicable @ 0.5% per week delay, maximum upto 5% of total contract value.

- Insurance

  - Contractor shall be responsible & shall arrange for all the necessary insurance coverage. The insurance shall include but not limited to following

    - Workman compensation/ESI & occupational illness insurance for all the plant staff/worker working under this contract.

    - The contractor should have GPA insurance for their worker & staff.

    - The full particulars of the contractor’s insurance shall be provided at the earliest opportunity for approval by the owner whose approval thereof not to be unreasonably withheld.

- Penalty Clause:

  - In case of failure to make payment to the workmen within 7 days after wage period in any month, penalty @ 1% of gross value of bill for corresponding period for which wage is due per day of default may  be imposed & deducted from the interim running bill maximum to the extent of 5% of the gross value of bill for the said period at the discretion of Owner . Repetition of such default for more than three times can lead for termination of the contract with 7 days advance notice to the contractor or HEL reserves all rights to pay the workmen under the contractor directly to avoid any work disruption and recover such cost with 20% overhead from the Contractor.

  - In case of non-submission of the Group Insurance Policy of the workmen engaged in the contract, penalty @ 5% of the contract value shall be imposed.

  - In case of failure to remove the scraps/debris within the stipulated period, the same shall be executed by other agencies at the cost and risk of the contractor and a penalty @1% of the contract value shall be imposed.

  - Non Availability of T&P: In case any work is delayed due to non-availability of Tools & Tackles / consumables which are in the scope of the Contractor, LD @ Rs. 2,000/- (Rupees Two Thousand Only) per instance shall be applicable. The LD amount shall be recovered from the Contractor's monthly RA bill. In case the Tools & Tackles / consumables which are in the scope of the Contractor are arranged by HEL to expedite the work, the cost of arranging the material / equipment shall be deducted / recovered from the Contractor's monthly RA bill at the rate prescribed by the HEL  EIC over and above said LD for non-availability. The decision of the HEL’s EIC shall be final in this regard.

  - Poor House Keeping at site: Penalty of Rs. 2,000.00 shall be imposed per instance if the housekeeping is not maintained properly by the contractor to the satisfaction of the EIC.

  - Serious Safety violation: Penalty of Rs. 1,000.00 shall be imposed per instance.

- Penalty for Fatal/Major/Minor Injury

In case of any injury or death due to the negligence of the contractor or his employees, workers, agents, representatives, and subcontractors, the contractor shall immediately deposit the following amount in lump sum to pay compensation to the aggrieved person : -

  - Fatal injury or accident causing death Penalty, Penalty Compensation of Rs. Ten (10) Lakh per person shall be borne by contractor.

  - Major injuries or accident causing 25% or more permanent disablement to workmen or employees –Penalty  Rs 1 Lakh, maximum Rs 5 lakhs depending on severity.

  - Minor injuries or accident leading to hospitalization- contractor has to pay regular wages during the period of sick leave due to injury/accident inside plant. Contractor shall liable to pay compensation amount of upto/maximum one lakh as per directives of HEL.